FALCON ELECTRONICS

CONFIGURATION MANAGEMENT PLAN

Project Alcatraz — SMT Production Line Installation

| Project Manager | Ricardo Palacio Serra |
| --- | --- |
| Prepared By | Ricardo Palacio Serra / Project Manager |
| Date | 01 / 09 / 2026 |
| Version | 1.0 |

1. Purpose & Overview

This Configuration Management Plan defines how configuration items — governing documents, technical specifications, design drawings, and quality records — are identified, versioned, baselined, and controlled throughout Project Alcatraz. Configuration control is a specific focus on this project because the new SMT line must be qualified against IATF 16949 requirements for Falcon Electronics' automotive customer, AutoDrive Systems Inc.; auditors will expect traceable version control over equipment specifications, acceptance criteria, and qualification records.

This plan works together with the companion Configuration Item Register, which lists every controlled item and its current version and baseline status. Configuration Management is distinct from Change Management: the Change Management Plan governs changes to Project Alcatraz's scope, schedule, and cost baselines broadly, while this plan governs version control of the specific deliverables and documents listed in Section 2.

2. Configuration Items

In Configuration Control:

| Category | Examples |
| --- | --- |
| Governing Documents | Project Charter, Project Scope Statement |
| Technical Deliverables | SMT line equipment specification (printer, pick-and-place, reflow oven), AOI system specification, electrical & compressed air design drawings, facility layout floor plan, MES integration configuration specification |
| Quality Records | IPC-A-610 Class 3 acceptance criteria, First Article Inspection (FAI) protocol, IATF 16949 internal pre-audit checklist |
| Regulatory Submissions | IATF 16949 qualification package submitted to AutoDrive Systems Inc. |

Not in Configuration Control:

Informal vendor email correspondence, internal working notes from status meetings, and draft training materials prior to being finalized for the Operator Training work package (4.2.1).

3. Identification & Naming Convention

| Element | Convention |
| --- | --- |
| Item ID Format | CI-###, sequential |
| Version Numbering | Major.Minor format — 1.0 for the first baseline, 1.1 for a minor revision, 2.0 for a major revision. Pre-baseline drafts use 0.x |
| File Naming Convention | Alcatraz_[ItemName]_v[Version]_[YYYYMMDD] |
| Draft vs. Baselined Marking | Files below version 1.0 are marked 'DRAFT' in the filename and carry a draft watermark until formally approved |

4. Baseline Management

An item is baselined once it has been reviewed and formally approved by its designated Configuration Owner (Section 8). Governing documents are approved by the Project Manager and Sponsor; technical specifications and design drawings are approved by their respective Configuration Owner; quality records and regulatory submissions are approved by the Quality Manager. Once baselined, further changes require a Change Log entry rather than direct editing.

5. Configuration Control Process

| Step | Description | Responsible |
| --- | --- | --- |
| 1. Request Change | Submit a change request for the baselined item via the Change Log | Requester |
| 2. Impact Assessment | Assess impact on dependent items, schedule, cost, and quality | Configuration Owner |
| 3. Approve / Reject | Review and decide per the Change Management Plan's approval thresholds | CCB / Approver |
| 4. Update & Re-Version | Update the item, increment its version number, and update the Configuration Item Register | Configuration Owner |
| 5. Communicate | Notify affected stakeholders of the new version | Ricardo Palacio Serra |

6. Configuration Status Accounting

The Configuration Item Register is the single source of truth for the current version and baseline status of every controlled item on Project Alcatraz. It is updated within 1 business day of any approved change, and is reviewed at each weekly project status meeting alongside the Risk Register and Change Log.

7. Configuration Audits

| Audit Type | Frequency | Purpose |
| --- | --- | --- |
| Functional Configuration Audit | Prior to First Article Inspection (target: mid-November 2026) | Confirms the SMT line performs per its baselined equipment specification and acceptance criteria |
| Physical Configuration Audit | Prior to the IATF 16949 internal pre-audit (target: mid-November 2026) | Confirms the as-built equipment and facility match their recorded configuration and documentation |

8. Roles & Responsibilities

| Role | Responsibility |
| --- | --- |
| Project Manager (Ricardo Palacio Serra) | Owns this Configuration Management Plan; ensures the Configuration Item Register stays current |
| Configuration Owner — Procurement (Mariana Solís) | Owns equipment technical specifications (printer, pick-and-place, reflow, AOI) |
| Configuration Owner — Facilities (Luis Beltrán) | Owns electrical & compressed air design drawings |
| Configuration Owner — Manufacturing (Fernando Ibarra) | Owns facility layout floor plan and operator training materials |
| Configuration Owner — IT Integration (Sofía Reyes) | Owns the MES integration configuration specification |
| Quality / Compliance Lead (Daniela Cortés) | Owns quality records and regulatory submissions; conducts configuration audits |

9. Approval Signatures

| Name / Role | Signature | Date |
| --- | --- | --- |
| Angélica Navarro / Sponsor |  |  |
| Ricardo Palacio Serra / Project Manager |  |  |
| Daniela Cortés / Quality Manager |  |  |

10. Version / Revision History

| Version | Date | Author | Change Description |
| --- | --- | --- | --- |
| 1.0 | 01/09/2026 | Ricardo Palacio Serra | Initial draft, developed during project kickoff workshop |