## EVM Tracker
[ORGANIZATION NAME]
EVM TRACKER
[Project Name / Title]
Budget at Completion (BAC): |  |  | 500000
Prepared By / Date: |  |  | [Name / Role] — [DD/MM/YYYY]
Period | Date | Planned Value (PV, cum.) | Earned Value (EV, cum.) | Actual Cost (AC, cum.) | CV (EV-AC) | SV (EV-PV) | CPI (EV/AC) | SPI (EV/PV) | EAC (BAC/CPI) | ETC (EAC-AC) | VAC (BAC-EAC)
1 | [Date 1] | 40000 | 38000 | 36000 | 2000 | -2000 | 1.0556 | 0.95 | 473684.2105 | 437684.2105 | 26315.7895
2 | [Date 2] | 85000 | 80000 | 78000 | 2000 | -5000 | 1.0256 | 0.94118 | 487500 | 409500 | 12500
3 | [Date 3] | 135000 | 122000 | 128000 | -6000 | -13000 | 0.95312 | 0.9037 | 524590.1639 | 396590.1639 | -24590.1639
4 | [Date 4] | 190000 | 175000 | 185000 | -10000 | -15000 | 0.94595 | 0.92105 | 528571.4286 | 343571.4286 | -28571.4286
5 | [Date 5] | 250000 | 228000 | 244000 | -16000 | -22000 | 0.93443 | 0.912 | 535087.7193 | 291087.7193 | -35087.7193
6 | [Date 6] | 310000 | 289000 | 305000 | -16000 | -21000 | 0.94754 | 0.93226 | 527681.6609 | 222681.6609 | -27681.6609
7 | [Date 7]
8 | [Date 8]
9 | [Date 9]
10 | [Date 10]
11 | [Date 11]
12 | [Date 12]
vitruvioconsultores.net

## Instructions
[ORGANIZATION NAME]
EVM TRACKER — INSTRUCTIONS & FORMULA REFERENCE
This tracker works together with the Cost Management Plan (Word document), which defines the full EVM methodology and control thresholds. Enter cumulative PV, EV, and AC for each reporting period; every other column (CV, SV, CPI, SPI, EAC, ETC, VAC) is calculated automatically from the BAC and those three inputs.
Column Reference
Planned Value (PV, cum.) | Cumulative budgeted cost of work scheduled to be complete by this period. INPUT.
Earned Value (EV, cum.) | Cumulative budgeted cost of work actually completed by this period. INPUT.
Actual Cost (AC, cum.) | Cumulative actual cost incurred by this period. INPUT.
CV (EV-AC) | Cost Variance. Positive = under budget; negative = over budget. CALCULATED.
SV (EV-PV) | Schedule Variance (in cost terms). Positive = ahead of schedule; negative = behind. CALCULATED.
CPI (EV/AC) | Cost Performance Index. Above 1.0 = under budget; below 1.0 = over budget. CALCULATED.
SPI (EV/PV) | Schedule Performance Index. Above 1.0 = ahead of schedule; below 1.0 = behind. CALCULATED.
EAC (BAC/CPI) | Estimate at Completion — projected total cost if current cost performance continues. CALCULATED.
ETC (EAC-AC) | Estimate to Complete — projected remaining cost to finish. CALCULATED.
VAC (BAC-EAC) | Variance at Completion — projected surplus (positive) or overrun (negative) at project end. CALCULATED.
CPI / SPI Threshold Legend
≥ 0.95 — On Track
0.90 – 0.94 — Watch
< 0.90 — Action Required
Reading the S-Curve Chart
If the EV line (navy) is below the PV line (grey dashed), the project is behind schedule. If the AC line (gold) is above the EV line, the project is over budget for the work completed so far. In a healthy project, EV and AC track closely together and both stay close to or above the PV line.
vitruvioconsultores.net