## WBS Dictionary
FALCON ELECTRONICS
WBS DICTIONARY
Project Alcatraz — SMT Production Line Installation
Prepared By: Ricardo Palacio Serra / Project Manager ¦ Date: 01/09/2026 ¦ Version: 1.0
WBS ID | Element Name | Level | Parent ID | Description | Deliverable(s) | Acceptance Criteria | Owner | Est. Duration | Est. Cost | Dependencies | Status
1.0 | Initiation & Planning | 1 |  | Project governance, charter approval, and facility/site readiness assessment for the SMT line installation. | Approved Charter; Facility Readiness Report | Sponsor sign-off obtained; facility constraints documented | Ricardo Palacio Serra | 10 days | 14000 |  | In Progress
1.1 | Project Charter & Governance | 2 | 1.0 | Formal authorization of the project and definition of governance structure. | Signed Project Charter; RACI Matrix | Charter signed by Sponsor; RACI agreed by core team | Ricardo Palacio Serra | 5 days | 6000 |  | In Progress
1.1.1 | Develop Project Charter | 3 | 1.1 | Draft, review, and obtain Sponsor sign-off on the Project Charter defining scope, objectives, budget, and timeline. | Signed Project Charter | Charter approved and signed by Angélica Navarro (Sponsor) | Ricardo Palacio Serra | 3 days | 4000 |  | Complete
1.1.2 | Establish Project Governance & RACI | 3 | 1.1 | Define roles, responsibilities, and decision authority across the core project team. | RACI Matrix | RACI Matrix reviewed and agreed by all named roles | Ricardo Palacio Serra | 2 days | 2000 | 1.1.1 | In Progress
1.2 | Site & Facility Assessment | 2 | 1.0 | Assessment of facility readiness and initiation of utility upgrade permitting. | Facility Readiness Report; Submitted Permit Applications | Facility constraints documented; permits submitted | Luis Beltrán | 5 days | 8000 | 1.1.1 | Not Started
1.2.1 | Conduct Facility Readiness Assessment | 3 | 1.2 | Assess existing floor space, power capacity, and compressed air supply against new line requirements. | Facility Readiness Report | Report identifies all gaps requiring upgrade before installation | Luis Beltrán | 3 days | 6000 | 1.1.1 | Not Started
1.2.2 | Obtain Utility Upgrade Permits | 3 | 1.2 | Submit and track permit applications for electrical and compressed air upgrades. | Approved Permits | All required permits approved by relevant authorities | Luis Beltrán | 15 days | 2000 | 1.2.1 | Not Started
2.0 | Procurement & Facility Preparation | 1 |  | Procurement of SMT equipment and preparation of the facility to receive and support it. | Delivered Equipment; Upgraded Facility | Equipment on-site; facility utilities and layout ready for installation | Ricardo Palacio Serra | 60 days | 1642000 | 1.0 | Not Started
2.1 | Equipment Procurement | 2 | 2.0 | Purchase order issuance and vendor management through delivery of all SMT equipment. | Delivered SMT Equipment | All equipment delivered to site and inspected for damage | Mariana Solís | 30 days | 1412000 | 1.1.1 | Not Started
2.1.1 | Issue Purchase Orders (Printer, Pick-and-Place, Reflow, AOI) | 3 | 2.1 | Issue POs to the selected equipment vendor for all core SMT line equipment. | Signed Purchase Orders | POs issued with contractual delivery date and penalty clause for delay | Mariana Solís | 10 days | 1400000 | 1.1.1 | Not Started
2.1.2 | Manage Vendor Delivery & Customs Clearance | 3 | 2.1 | Track shipment, coordinate customs clearance, and confirm on-site delivery. | Delivered Equipment | Equipment received on-site and inspected with no shipping damage | Mariana Solís | 20 days | 12000 | 2.1.1 | Not Started
2.2 | Facility Preparation | 2 | 2.0 | Utility upgrades and layout modifications to prepare the facility for the new line. | Upgraded Utilities; Modified Floor Layout | Utilities pass inspection; layout matches approved facility plan | Luis Beltrán | 30 days | 230000 | 1.2.2 | Not Started
2.2.1 | Electrical & Compressed Air Upgrades | 3 | 2.2 | Install additional electrical capacity and compressed air lines required by the new equipment. | Upgraded Electrical & Air Systems | Systems pass electrical safety and pressure inspection | Luis Beltrán | 20 days | 140000 | 1.2.2 | Not Started
2.2.2 | Facility Layout & Floor Modifications | 3 | 2.2 | Modify production floor layout, flooring, and ESD control zones for the new line. | Modified Production Floor | Floor layout matches approved facility plan; ESD zones certified | Fernando Ibarra | 15 days | 90000 | 2.2.1 | Not Started
3.0 | Installation & Integration | 1 |  | Physical installation of SMT equipment and integration with the MES/ERP systems. | Installed & Integrated SMT Line | Line mechanically installed and passing MES integration tests | Ricardo Palacio Serra | 35 days | 78000 | 2.0 | Not Started
3.1 | Equipment Installation | 2 | 3.0 | Mechanical installation of the SMT printer, pick-and-place, reflow oven, and AOI system. | Installed SMT Equipment | All equipment installed, powered on, and passing vendor commissioning checks | Carlos Medina | 20 days | 50000 | 2.1.2, 2.2.2 | Not Started
3.1.1 | Install SMT Printer, Pick-and-Place, and Reflow Oven | 3 | 3.1 | Physical installation and mechanical setup of the core SMT line equipment. | Installed Core Equipment | Equipment installed per vendor specification and powered on successfully | Carlos Medina | 15 days | 35000 | 2.1.2, 2.2.2 | Not Started
3.1.2 | Install Automated Optical Inspection (AOI) System | 3 | 3.1 | Physical installation and calibration of the AOI system at the end of the line. | Installed AOI System | AOI system installed, calibrated, and passing vendor commissioning checks | Carlos Medina | 10 days | 15000 | 3.1.1 | Not Started
3.2 | MES / ERP Integration | 2 | 3.0 | Integration of the new line with Falcon's Manufacturing Execution System and ERP. | Integrated MES Interface | Line data flows correctly into MES/ERP with no traceability gaps | Sofía Reyes | 15 days | 28000 | 3.1.1 | Not Started
3.2.1 | Configure MES Data Interfaces | 3 | 3.2 | Configure MES/ERP data interfaces for the new line's production and quality data. | Configured MES Interface | MES interface configured and passing initial connectivity tests | Sofía Reyes | 10 days | 20000 | 3.1.1 | Not Started
3.2.2 | Conduct Integration Testing (UAT) | 3 | 3.2 | User acceptance testing of the MES/ERP integration in a staging environment before go-live. | UAT Test Results | All critical UAT test cases pass with no traceability gaps | Sofía Reyes | 5 days | 8000 | 3.2.1 | Not Started
4.0 | Qualification & Ramp-Up | 1 |  | Process qualification, quality audit readiness, operator training, and ramp-up to full production. | Qualified, Fully Ramped-Up Production Line | Line qualified, achieving throughput and yield targets, formally accepted | Ricardo Palacio Serra | 40 days | 64000 | 3.0 | Not Started
4.1 | Process Qualification | 2 | 4.0 | Formal qualification of the line through First Article Inspection and an internal quality pre-audit. | FAI Report; Internal Audit Report | FAI passed; no major nonconformances open from internal pre-audit | Daniela Cortés | 15 days | 13000 | 3.1.2, 3.2.2 | Not Started
4.1.1 | Conduct First Article Inspection (FAI) | 3 | 4.1 | Conduct and document First Article Inspection to confirm the line meets quality requirements. | FAI Report | FAI passed against IPC-A-610 Class 3 and customer specifications | Daniela Cortés | 8 days | 7000 | 3.1.2, 3.2.2 | Not Started
4.1.2 | IATF 16949 Internal Pre-Audit | 3 | 4.1 | Conduct an internal pre-audit against IATF 16949 requirements ahead of the customer's qualification audit. | Internal Pre-Audit Report | No major nonconformances open at time of customer audit | Daniela Cortés | 10 days | 6000 | 4.1.1 | Not Started
4.2 | Production Ramp-Up & Closure | 2 | 4.0 | Operator training, ramp-up to full throughput, and formal project closure. | Trained Operators; Ramped-Up Line; Closed Project | 3,500 boards/day sustained; FPY >98%; project formally closed | Fernando Ibarra | 30 days | 51000 | 4.1.1 | Not Started
4.2.1 | Operator Training | 3 | 4.2 | Train production operators on the new line, in parallel with installation and qualification. | Trained Operator Roster | All assigned operators certified on the new line's operating procedures | Fernando Ibarra | 15 days | 40000 | 3.1.1 | Not Started
4.2.2 | Production Ramp-Up to Full Throughput | 3 | 4.2 | Progressive ramp-up of production volume to the sustained target throughput. | Ramp-Up Production Data | 3,500 boards/day sustained over a continuous 2-week run; FPY >98% | Fernando Ibarra | 18 days | 8000 | 4.1.1, 4.2.1 | Not Started
4.2.3 | Project Closure & Handover | 3 | 4.2 | Formal closure of the project, including handover to production operations. | Final Report; Signed Acceptance | Sponsor and Plant Manager sign-off obtained; Final Report distributed | Ricardo Palacio Serra | 5 days | 3000 | 4.2.2, 4.1.2 | Not Started
vitruvioconsultores.net
[7 empty] | Total (Level 1 phases only): |  | 1798000