## Project Schedule
[ORGANIZATION NAME]
PROJECT SCHEDULE
[Project Name / Title]
Prepared By: [Name / Role] ¦ Date: [DD/MM/YYYY] ¦ Version: [1.0]
ID | WBS | Task Name | Duration (days) | Start | Finish | % Complete | Predecessors | Resource Names | Milestone | Summary | 2025-01-06 | 2025-01-13 | 2025-01-20 | 2025-01-27 | 2025-02-03 | 2025-02-10 | 2025-02-17 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-21
1 | 1 | Project Kickoff | 0 | 2025-01-06 | 2025-01-06 | 100% |  | [Sponsor / PM] | Yes | No
2 | 1.1 | Initiation Phase | 10 | 2025-01-07 | 2025-01-16 | 100% |  |  | No | Yes
3 | 1.1.1 | Develop Project Charter | 5 | 2025-01-07 | 2025-01-11 | 100% | 1 | [PM] | No | No
4 | 1.1.2 | Stakeholder Identification | 5 | 2025-01-12 | 2025-01-16 | 100% | 3 | [Business Analyst] | No | No
5 | 1.2 | Planning Phase | 10 | 2025-01-17 | 2025-01-26 | 60% |  |  | No | Yes
6 | 1.2.1 | Requirements Gathering | 5 | 2025-01-17 | 2025-01-21 | 80% | 4 | [Business Analyst] | No | No
7 | 1.2.2 | Risk Planning | 5 | 2025-01-22 | 2025-01-26 | 40% | 6 | [PM] | No | No
8 | 1.2.3 | Baseline Approved | 0 | 2025-01-27 | 2025-01-27 | 0% | 7 | [Sponsor] | Yes | No
9 | 2 | Execution Phase | 30 | 2025-01-28 | 2025-02-26 | 0% |  |  | No | Yes
10 | 2.1 | Development / Build | 15 | 2025-01-28 | 2025-02-11 | 0% | 8 | [Delivery Team] | No | No
11 | 2.2 | Testing | 10 | 2025-02-12 | 2025-02-21 | 0% | 10 | [QA Team] | No | No
12 | 2.3 | UAT Sign-off | 0 | 2025-02-22 | 2025-02-22 | 0% | 11 | [Sponsor] | Yes | No
13 | 3 | Closing Phase | 10 | 2025-02-23 | 2025-03-04 | 0% |  |  | No | Yes
14 | 3.1 | Deployment | 5 | 2025-02-23 | 2025-02-27 | 0% | 12 | [Delivery Team] | No | No
15 | 3.2 | Lessons Learned & Closeout | 4 | 2025-02-28 | 2025-03-03 | 0% | 14 | [PM] | No | No
16 | 3.3 | Project Closure | 0 | 2025-03-04 | 2025-03-04 | 0% | 15 | [Sponsor / PM] | Yes | No
vitruvioconsultores.net

## Instructions
[ORGANIZATION NAME]
PROJECT SCHEDULE — INSTRUCTIONS & MS PROJECT IMPORT GUIDE
This workbook is a detailed project schedule with a built-in Gantt view (via conditional formatting), pre-filled with an illustrative sample schedule you should replace with your own tasks. Columns are named to match the fields Microsoft Project expects on import, so this file can be opened directly in MS Project and mapped with minimal effort.
Column Reference
ID | Sequential task number (matches MS Project's own internal Task ID).
WBS | Hierarchical outline number (e.g., 1, 1.1, 1.1.1) reflecting the Work Breakdown Structure.
Task Name | The task or summary/phase title. Indented by outline level for readability.
Duration (days) | Length of the task in calendar days. Use 0 for milestones.
Start / Finish | Task dates. Finish is calculated as Start + Duration - 1 (or equal to Start for milestones).
% Complete | Progress against the task.
Predecessors | Task ID(s) this task depends on. Multiple predecessors can be comma-separated.
Resource Names | Assigned resource(s) — this column name matches MS Project's own field exactly.
Milestone | Yes/No flag used to color the Gantt marker gold. Set Duration to 0 for true milestones.
Summary | Yes/No flag marking a row as a phase/summary task — shaded row and dark navy Gantt bar.
Gantt Legend
Summary / Phase bar
Task bar
Milestone
How to Import This File into Microsoft Project
1. In Microsoft Project, go to File > Open, then browse to this .xlsx file.
2. Project launches the Import Wizard automatically for Excel files.
3. Choose 'New Map' (or 'Project Excel Template' if offered) and map the source worksheet as 'Project Schedule'.
4. Map columns to Project fields: Task Name -> Name, Duration -> Duration, Start -> Start, Finish -> Finish, % Complete -> % Complete, Predecessors -> Predecessors, Resource Names -> Resource Names, WBS -> WBS or Outline Number.
5. The Milestone and Summary columns do not need to be mapped -- Project detects milestones automatically when Duration = 0, and detects summary tasks automatically from the outline/indent structure once WBS levels are mapped.
6. After import, review the schedule in Project -- Project will recalculate dates based on Predecessors and Duration using its own scheduling engine, which may adjust the illustrative dates from this Excel file.
Note: This Excel file does not have a scheduling engine -- Start/Finish dates here are static values, not automatically recalculated when you change Predecessors or Duration (Finish is the only live formula: Start + Duration - 1). For live dependency-driven rescheduling, import into Microsoft Project as described above.
vitruvioconsultores.net