## Resource Assignment Matrix
[ORGANIZATION NAME]
RESOURCE ASSIGNMENT MATRIX
[Project Name / Title]
Prepared By: [Name / Role] ¦ Date: [DD/MM/YYYY] ¦ Version: [1.0]
Resource Name | Role | Type | Cost Rate (per period) | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Avg. Allocation
[Resource 1] | [Project Manager] | Internal | 8000 | 100 | 100 | 100 | 100 | 100 | 100 | 100
[Resource 2] | [Technical Lead] | Internal | 7000 | 50 | 100 | 100 | 120 | 80 | 0 | 75
[Resource 3] | [Contractor / Specialist] | Contractor | 12000 | 0 | 0 | 100 | 100 | 100 | 0 | 50
| Over-allocation check (any cell > 100%) → |  |  | OK | OK | OK | Over-allocated | OK | OK
vitruvioconsultores.net

## Instructions
[ORGANIZATION NAME]
RESOURCE ASSIGNMENT MATRIX — INSTRUCTIONS & LEGEND
This matrix tracks each resource's percentage allocation to the project, period by period (months shown here, but can be adjusted to weeks or Sprints). It works together with the Resource Management Plan (Word document), which defines the methodology for acquiring, developing, and releasing resources.
Column Reference
Resource Name | The individual (or named equipment) being tracked.
Role | Their role on this project — should align with the RACI Matrix and WBS Dictionary owner fields.
Type | Internal, Contractor, or Equipment.
Cost Rate (per period) | Cost per period at 100% allocation — used to estimate resource cost alongside the Cost Baseline.
Month 1...Month N | Percentage allocation to this project for that period. 100% = full-time; 50% = half-time; 0% = not allocated that period. Enter numbers only (e.g., 100, not '100%').
Avg. Allocation | Calculated automatically — the average allocation percentage across all periods shown.
Allocation Color Legend
> 100% — Over-allocated
100% — Fully allocated
1-99% — Partially allocated
0% — Not allocated this period
Using the Over-Allocation Check Row
The row below the resource list automatically flags any period where at least one resource exceeds 100% allocation. 'Over-allocated' (red) means you need to either reduce that resource's commitment elsewhere, bring in additional help, or adjust the schedule for that period -- do not simply accept a resource shown above 100% as sustainable.
vitruvioconsultores.net