FALCON ELECTRONICS

PROJECT CHARTER

Project Alcatraz — SMT Production Line Installation

| Project Sponsor | Angélica Navarro / VP of Operations |
| --- | --- |
| Project Manager | Ricardo Palacio Serra |
| Prepared By | Ricardo Palacio Serra / Project Manager |
| Date | 01 / 09 / 2026 |
| Version | 1.0 |

1. Project Title & Description

Project Name:

Project Alcatraz — SMT Production Line Installation

Description:

Falcon Electronics, a contract electronics manufacturing (EMS) provider, will install a new Surface Mount Technology (SMT) production line at its main manufacturing facility. The project covers the procurement, installation, and qualification of solder paste printing, pick-and-place, reflow oven, and automated optical inspection (AOI) equipment, and its integration with the facility's existing Manufacturing Execution System (MES). The new line will expand Falcon's production capacity to support a newly signed automotive electronics customer contract.

2. Purpose / Business Justification

Falcon Electronics has secured a multi-year supply agreement with a new automotive electronics customer that requires production volumes exceeding the throughput of the facility's current SMT lines. Without additional capacity, Falcon risks missing contractual delivery commitments and losing the opportunity to grow its footprint in the automotive EMS segment. This project directly supports the company's strategic goal of growing automotive-sector revenue by 25% over the next two fiscal years, and secures Falcon's position as a qualified, capacity-ready supplier for future automotive programs.

3. Measurable Objectives & Success Criteria

| Objective | Success Criteria |
| --- | --- |
| Install and qualify the new SMT line within 4 months (by December 31, 2026) | Line is operational and passes First Article Inspection (FAI) by the target date |
| Achieve sustained production throughput of 3,500 boards/day at full capacity | Throughput validated over a continuous 2-week production run |
| Achieve first-pass yield (FPY) greater than 98% | FPY confirmed by AOI and functional test data during ramp-up |

4. High-Level Requirements

The new line must integrate with Falcon's existing MES and ERP systems for real-time production tracking and traceability.

The line must meet IPC-A-610 Class 3 workmanship standards required for automotive electronics assemblies.

All qualifying equipment and processes must meet IATF 16949 requirements applicable to the automotive customer's program.

5. High-Level Project Description & Boundaries

In Scope:

Procurement and installation of SMT equipment (solder paste printer, pick-and-place, reflow oven, AOI system); facility modifications required to support the new line (electrical power, compressed air, ventilation); equipment qualification and process validation; operator training; and integration with the MES.

Out of Scope:

Construction of new facility space or building expansion; procurement of production raw material inventory beyond initial qualification runs; and recruitment of new operating staff beyond training of existing production personnel.

6. High-Level Risks

| Risk Description | Likelihood | Impact |
| --- | --- | --- |
| Equipment delivery delay from the selected equipment supplier | Medium | High |
| Facility utility upgrades (power / compressed air) take longer than planned | Medium | Medium |
| Operator training and production ramp-up progress slower than expected, delaying yield targets | Low | Medium |

7. Summary Milestone Schedule

| Milestone | Target Date |
| --- | --- |
| Project Kickoff | September 1, 2026 |
| Equipment Procurement Complete / Delivered to Site | September 30, 2026 |
| Facility Preparation & Equipment Installation Complete | October 31, 2026 |
| Equipment Qualification & First Article Inspection | November 30, 2026 |
| Production Ramp-Up Complete & Project Closure | December 31, 2026 |

8. Summary Budget

| Estimated Total Budget | USD $1,850,000 |
| --- | --- |
| Funding Source | Capital Expenditure Budget — Operations Expansion Fund |
| Budget Notes / Assumptions | Includes SMT equipment (~$1.4M), facility modifications (~$250K), training and process qualification (~$100K), and contingency reserve (~$100K, ~5% of total budget). |

9. Stakeholder List

| Name | Role | Interest / Influence | Dept. |
| --- | --- | --- | --- |
| Angélica Navarro | Project Sponsor / VP Operations | High / High | Operations |
| Ricardo Palacio Serra | Project Manager | High / High | PMO |
| Fernando Ibarra | Plant Manager | High / Medium | Manufacturing |
| Daniela Cortés | Quality Manager | Medium / High | Quality Assurance |
| Luis Beltrán | Facilities Engineer | Medium / Medium | Facilities |
| James Whitfield | Customer Program Manager (AutoDrive Systems Inc.) | Medium / High | Customer |

10. Project Approval Requirements

The project is considered successful when the SMT line is fully qualified, achieves the throughput and first-pass yield targets defined in Section 3, and passes First Article Inspection. Formal acceptance requires sign-off from the Project Sponsor (Angélica Navarro) based on the Quality Manager's review of qualification and FAI reports. Final project closure additionally requires sign-off from the Plant Manager confirming the line has been fully transitioned to production operations.

11. Assigned Project Manager & Authority Level

| Project Manager | Ricardo Palacio Serra |
| --- | --- |
| Authority Level | Authorized to approve project expenditures up to USD $50,000 without additional sponsor approval, manage vendor and contractor agreements within the approved budget, and make day-to-day resource assignment decisions for the project team. |

12. Sponsor Name & Authority

| Sponsor | Angélica Navarro / VP of Operations |
| --- | --- |
| Authority | Full authority to authorize project funding up to the approved budget, approve scope changes, resolve escalations beyond the Project Manager's authority, and represent the project to executive leadership. |

13. Assumptions & Constraints

Assumptions:

Facility floor space for the new line is available and has been pre-approved by Facilities; the selected equipment vendor can meet the proposed delivery schedule; and the existing workforce can be trained to operate the new line without the need for additional hires.

Constraints:

The project timeline is fixed at 4 months, tied to the automotive customer's contractual production start date; the capital budget is capped at USD $1,850,000; and installation activities must not disrupt production on Falcon's existing SMT lines.

14. Project Team / Organization Structure (Optional)

The Project Manager reports directly to the Project Sponsor (VP of Operations). The cross-functional project team includes representatives from Facilities, Quality Assurance, Manufacturing Engineering, and IT/MES Integration, each assigned by their respective department lead to support the project through installation and qualification.

15. Communication Requirements (Optional)

Weekly status meetings with the core project team; bi-weekly steering committee updates to the Project Sponsor; a monthly executive summary report to senior leadership; and ad hoc escalation communications for any risk or issue threatening the critical path.

16. Approval Signatures

| Name / Role | Signature | Date |
| --- | --- | --- |
| Angélica Navarro / Sponsor |  |  |
| Ricardo Palacio Serra / Project Manager |  |  |
| Fernando Ibarra / Plant Manager |  |  |

17. Version / Revision History

| Version | Date | Author | Change Description |
| --- | --- | --- | --- |
| 1.0 | 01/09/2026 | Ricardo Palacio Serra | Initial draft |