## RACI Matrix
[ORGANIZATION NAME]
RACI MATRIX
[Project Name / Title]
Prepared By: [Name / Role] ¦ Date: [DD/MM/YYYY] ¦ Version: [1.0]
Activity ID | Activity / Deliverable | Phase | [Sponsor] | [Project Manager] | [Business Analyst] | [Technical Lead] | [QA Lead] | [Procurement Lead] | [Key Stakeholder / Customer] | # of 'A' (should = 1)
ACT-001 | Develop Project Charter | Initiating | A | R | C |  |  |  | I | 1
ACT-002 | Approve Business Case | Initiating | A | R | C |  |  |  | I | 1
ACT-003 | Gather Requirements | Planning | I | A | R | C |  |  | C | 1
ACT-004 | Design Solution | Planning | I | A | R | C | C |  |  | 1
ACT-005 | Procure Equipment / Vendor Contracts | Planning | A | R |  | C |  | R |  | 1
ACT-006 | Develop / Build Deliverables | Executing | I | A | C | R | C |  |  | 1
ACT-007 | Test / Quality Assurance | Executing | I | C | C | C | R/A |  | I | 1
ACT-008 | Risk Management | Monitoring & Controlling | A | R | C | C | C |  | I | 1
ACT-009 | Change Control Decisions | Monitoring & Controlling | A | R | C | C | C | C | I | 1
ACT-010 | Final Acceptance & Sign-off | Closing | A | R | I | I | C |  | R | 1
ACT-011 | Project Closure | Closing | A | R | I | I | I | I | I | 1
ACT-012 | [9 empty] | 0
ACT-013 | [9 empty] | 0
ACT-014 | [9 empty] | 0
ACT-015 | [9 empty] | 0
Validation: count of 'A' per row should always equal 1 →
vitruvioconsultores.net

## Instructions
[ORGANIZATION NAME]
RACI MATRIX — INSTRUCTIONS & LEGEND
This matrix works together with the Roles & Responsibilities document (Word), which defines the RACI legend and role descriptions in full. Each row is an activity/deliverable; each column is a role. Enter exactly one R/A/C/I combination per cell -- use 'R/A' only when the same role is both doing the work and accountable for it (common on very small teams).
RACI Legend
R | Responsible | Does the work. Multiple R's allowed per activity.
A | Accountable | Owns the outcome, final sign-off. Exactly ONE per activity -- never zero, never more than one.
C | Consulted | Two-way input sought before/during the activity.
I | Informed | One-way update after the activity; no input required.
Using the Validation Column
The rightmost column ('# of A') automatically counts how many Accountable assignments exist per row. It should always show 1 (highlighted green). If it shows 0 or 2+ (highlighted red), that activity has no clear owner, or has conflicting ownership -- resolve this before finalizing the matrix.
vitruvioconsultores.net