FALCON ELECTRONICS

RISK MANAGEMENT PLAN

Project Alcatraz — SMT Production Line Installation

| Project Manager | Ricardo Palacio Serra |
| --- | --- |
| Prepared By | Ricardo Palacio Serra / Project Manager |
| Date | 01 / 09 / 2026 |
| Version | 1.0 |

1. Purpose & Overview

This Risk Management Plan defines how risk management activities will be structured and performed for Project Alcatraz, the installation and qualification of a new SMT production line at Falcon Electronics' main manufacturing facility. It defines the methodology used to populate and maintain the companion Risk Register, which is the working, living tracking tool used throughout the 4-month installation period (September 1 – December 31, 2026).

2. Roles & Responsibilities

| Role | Responsibility |
| --- | --- |
| Project Sponsor (Angélica Navarro) | Approves risk thresholds, contingency reserve use, and escalations beyond the Project Manager's authority |
| Project Manager (Ricardo Palacio Serra) | Owns the Risk Register, facilitates identification/analysis, and tracks responses through closure |
| Risk Owners | Individual owners assigned per risk (e.g., Facilities Engineer for utility risks, Quality Manager for qualification risks) — accountable for monitoring and executing the response plan |
| Risk Review Board | Monthly steering committee of the Sponsor, Plant Manager, and Project Manager, reviewing high-severity risks |
| Project Team | Identifies and reports new risks as they emerge during installation and qualification |

3. Risk Categories (Risk Breakdown Structure)

| Category | Examples for This Project |
| --- | --- |
| Technical | SMT equipment integration, MES/ERP data integration, ESD and contamination control |
| External | Equipment vendor delivery and customs/import timelines, customer (AutoDrive Systems Inc.) requirement changes, IATF 16949 audit outcomes |
| Organizational | Facilities permitting and utility upgrade timelines, staffing availability for installation and training |
| Project Management | Schedule compression against the fixed 4-month window, coordination across Facilities/Quality/IT workstreams |

4. Probability & Impact Definitions

Probability Scale:

| Score | Rating | Definition |
| --- | --- | --- |
| 1 | Very Low | <10% chance of occurring during the project |
| 2 | Low | 10–30% chance of occurring |
| 3 | Medium | 30–50% chance of occurring |
| 4 | High | 50–70% chance of occurring |
| 5 | Very High | >70% chance of occurring |

Impact Scale (by objective, relative to this project's baselines):

| Score | Rating | Schedule (4-month window) | Cost ($1.85M budget) | Quality |
| --- | --- | --- | --- | --- |
| 1 | Very Low | No impact to milestones | Negligible | No impact on FPY/qualification |
| 2 | Low | <3 days slip, absorbed in schedule | <3% budget (~$55K) | Minor rework, no FAI impact |
| 3 | Medium | 3–7 day slip to a milestone | 3–7% budget (~$55K–$130K) | Delays qualification by <1 week |
| 4 | High | 1–2 week slip; threatens Dec 31 close | 7–15% budget (~$130K–$280K) | FAI/customer qualification at risk |
| 5 | Very High | >2 week slip; misses customer start date | >15% budget (>$280K) | Line fails qualification / FPY target |

5. Probability & Impact Matrix and Risk Scoring

Risk Score = Probability × Impact (1–25). Severity thresholds used in the Risk Register:

| Risk Score Range | Severity | Typical Response Approach |
| --- | --- | --- |
| 1 – 6 | Low | Monitor; accept or apply low-cost mitigation |
| 7 – 14 | Medium | Actively manage; assign owner and response plan |
| 15 – 25 | High | Escalate; requires Sponsor/Steering Committee visibility and a documented response plan |

6. Risk Response Strategies

Strategies for Threats:

| Strategy | Description |
| --- | --- |
| Avoid | Eliminate the threat or protect the project from its impact |
| Transfer | Shift ownership of the threat to a third party, e.g., vendor penalty clauses, insurance |
| Mitigate | Reduce the probability and/or impact of the threat |
| Accept | Acknowledge the risk; no proactive action unless it occurs |
| Escalate | Refer to the Sponsor or Steering Committee to manage |

7. Risk Register Structure (Companion Spreadsheet)

The Risk Register is maintained as a separate, living spreadsheet (Risk_Register_Alcatraz_Falcon.xlsx), containing the fields defined in the standard Vitruvio Risk Register template: Risk ID, Category, Risk Description, Date Identified/Identified By, Probability/Impact, Risk Score/Severity, Response Strategy, Response/Mitigation Plan, Owner, Status, Trigger/Early Warning Sign, Residual Risk, and Last Updated.

8. Contingency & Management Reserves

Contingency Reserve (for identified/known risks):

USD $100,000 (approximately 5% of the total project budget), held by the Project Manager and released against specific identified risks in the Risk Register upon Sponsor notification.

Management Reserve (for unknown/unforeseen risks):

USD $55,500 (approximately 3% of the total project budget), held by the Project Sponsor and released only for risks not anticipated in the current Risk Register.

9. Risk Review & Reporting Cadence

| Activity | Frequency | Participants |
| --- | --- | --- |
| Risk Register Review | Weekly | Project Manager, Risk Owners |
| High-Severity Risk Escalation Review | Monthly (or ad hoc for High severity) | Sponsor, Plant Manager, Project Manager |
| Risk Register Update / Refresh | Bi-weekly | Project Manager |

10. Escalation Thresholds

Any risk scoring 15 or above must be escalated to the Project Sponsor within 48 hours of identification or re-scoring. Specifically for this project: any confirmed equipment delivery slip beyond 2 weeks, or any facility permitting delay affecting the October 31 installation milestone, must be escalated immediately regardless of computed score.

11. Approval Signatures

| Name / Role | Signature | Date |
| --- | --- | --- |
| Angélica Navarro / Sponsor |  |  |
| Ricardo Palacio Serra / Project Manager |  |  |
| Fernando Ibarra / Plant Manager |  |  |

12. Version / Revision History

| Version | Date | Author | Change Description |
| --- | --- | --- | --- |
| 1.0 | 01/09/2026 | Ricardo Palacio Serra | Initial draft |