## Risk Register
[ORGANIZATION NAME]
RISK REGISTER
[Project Name / Title]
Prepared By: [Name / Role] ¦ Date: [DD/MM/YYYY] ¦ Version: [1.0]
Risk ID | Category | Risk Description (Cause → Risk → Effect) | Date Identified | Identified By | Probability (1-5) | Impact (1-5) | Risk Score | Severity | Response Strategy | Response / Mitigation Plan | Owner | Status | Trigger / Early Warning Sign | Residual Risk | Last Updated
R-001 | Technical | [Cause] leads to [Risk], resulting in [Effect] | [Date] | [Name] | 4 | 4 | 16 | High | Mitigate | [Specific mitigation actions] | [Owner] | Open | [Early warning sign] | [Residual risk level after response] | [Date]
R-002
R-003
R-004
R-005
R-006
R-007
R-008
R-009
R-010
R-011
R-012
R-013
R-014
R-015
vitruvioconsultores.net

## Instructions
[ORGANIZATION NAME]
RISK REGISTER — INSTRUCTIONS & SCORING MODEL
This Risk Register works together with the Risk Management Plan, which defines the full methodology. Risk Score is calculated automatically as Probability x Impact (1-5 each, so Score ranges 1-25). Severity is derived automatically from the Score using the thresholds below.
Severity Thresholds (Risk Score = Probability x Impact)
Score Range | Severity | Guidance
1 – 6 | Low | Monitor; accept or apply low-cost mitigation.
7 – 14 | Medium | Actively manage; assign owner and response plan.
15 – 25 | High | Escalate; requires sponsor/steering committee visibility.
Column Reference
Risk ID | Unique identifier (e.g., R-001).
Category | Per the Risk Breakdown Structure: Technical, External, Organizational, Project Management.
Risk Description | Cause → Risk → Effect statement.
Date Identified / Identified By | Traceability of when and by whom the risk was raised.
Probability / Impact | 1-5 scores, defined in the Risk Management Plan, Section 4.
Risk Score / Severity | Calculated automatically (Probability x Impact; Low/Medium/High).
Response Strategy | Avoid, Transfer, Mitigate, Accept, Escalate (threats) or Exploit, Share, Enhance, Accept, Escalate (opportunities).
Response / Mitigation Plan | Specific actions to execute the chosen strategy.
Owner | Individual accountable for monitoring and executing the response.
Status | Open, In Progress, Closed, Occurred, or Escalated.
Trigger / Early Warning Sign | Indicator that the risk is about to occur.
Residual Risk | Remaining risk level after the response is applied.
Last Updated | Date of the most recent review.
vitruvioconsultores.net