## WBS Dictionary
[ORGANIZATION NAME]
WBS DICTIONARY
[Project Name / Title]
Prepared By: [Name / Role] ¦ Date: [DD/MM/YYYY] ¦ Version: [1.0]
WBS ID | Element Name | Level | Parent ID | Description | Deliverable(s) | Acceptance Criteria | Owner | Est. Duration | Est. Cost | Dependencies | Status
1.0 | [Phase / Major Deliverable 1] | 1 |  | [High-level description of this phase] | [6 empty] | Not Started
1.1 | [Deliverable 1.1] | 2 | 1.0 | [Description of this deliverable] | [6 empty] | Not Started
1.1.1 | [Work Package 1.1.1] | 3 | 1.1 | [Description of the work involved] | [Deliverable(s) produced] | [Criteria for acceptance] | [Owner] | [Days] | [Amount] | [Predecessor WBS ID(s)] | Not Started
1.1.2 | [Work Package 1.1.2] | 3 | 1.1 | [Description of the work involved] | [Deliverable(s) produced] | [Criteria for acceptance] | [Owner] | [Days] | [Amount] | [Predecessor WBS ID(s)] | Not Started
[ID]
[ID]
[ID]
[ID]
[ID]
[ID]
[ID]
[ID]
[ID]
[ID]
[ID]
vitruvioconsultores.net

## Instructions
[ORGANIZATION NAME]
WBS DICTIONARY — INSTRUCTIONS & LEGEND
The WBS Dictionary provides the detailed definition behind every element of the WBS shown in the companion Word document. One row per WBS element -- Phase and Deliverable rows (Levels 1-2) may only need a description, while Work Package rows (Level 3, the lowest level) should have every column completed, since that is where estimates and ownership are assigned.
Column Reference
WBS ID | The hierarchical code (e.g., 1.0, 1.1, 1.1.1), matching the Word document's WBS Outline exactly.
Element Name | Name of the phase, deliverable, or work package. Should be a noun (a deliverable), not a verb (an activity).
Level | 1 = Phase, 2 = Deliverable, 3 = Work Package (or 4, if a project uses an additional decomposition level).
Parent ID | The WBS ID of the element directly above this one in the hierarchy.
Description | What this element covers -- enough detail that someone unfamiliar with the project understands its boundaries.
Deliverable(s) | The tangible output(s) this work package produces. Typically only completed at Level 3.
Acceptance Criteria | What must be true for this work package to be considered complete and accepted.
Owner | The single individual accountable for this work package (should align with the RACI Matrix's 'A' assignment).
Est. Duration / Est. Cost | Estimates at the work package level, which roll up to form the Project Schedule and Cost Baseline.
Dependencies | Other WBS IDs (or external dependencies) this element depends on.
Status | Not Started, In Progress, or Complete.
Status Legend
Not Started
In Progress
Complete
vitruvioconsultores.net