FALCON ELECTRONICS

WORK BREAKDOWN STRUCTURE

Project Alcatraz — SMT Production Line Installation

| Project Manager | Ricardo Palacio Serra |
| --- | --- |
| Prepared By | Ricardo Palacio Serra / Project Manager |
| Date | 01 / 09 / 2026 |
| Version | 1.0 |

1. Purpose & Overview

This Work Breakdown Structure decomposes the full scope of Project Alcatraz — the installation and qualification of a new SMT production line at Falcon Electronics' main manufacturing facility — into four phases and eleven work packages. It is the backbone for the Project Schedule, Cost Baseline, and RACI Matrix: every task, cost estimate, and role assignment traces back to a WBS element defined here. The WBS was developed through a decomposition workshop with the Project Manager, Plant Manager, Facilities Engineer, Quality Manager, and IT Integration Lead during project kickoff.

2. WBS Outline

The hierarchical breakdown of Project Alcatraz, from Level 1 (phase) down to Level 3 (work package).

1.0  Initiation & Planning

1.1  Project Charter & Governance

1.1.1  Develop Project Charter

1.1.2  Establish Project Governance & RACI

1.2  Site & Facility Assessment

1.2.1  Conduct Facility Readiness Assessment

1.2.2  Obtain Utility Upgrade Permits

2.0  Procurement & Facility Preparation

2.1  Equipment Procurement

2.1.1  Issue Purchase Orders (Printer, Pick-and-Place, Reflow, AOI)

2.1.2  Manage Vendor Delivery & Customs Clearance

2.2  Facility Preparation

2.2.1  Electrical & Compressed Air Upgrades

2.2.2  Facility Layout & Floor Modifications

3.0  Installation & Integration

3.1  Equipment Installation

3.1.1  Install SMT Printer, Pick-and-Place, and Reflow Oven

3.1.2  Install Automated Optical Inspection (AOI) System

3.2  MES / ERP Integration

3.2.1  Configure MES Data Interfaces

3.2.2  Conduct Integration Testing (UAT)

4.0  Qualification & Ramp-Up

4.1  Process Qualification

4.1.1  Conduct First Article Inspection (FAI)

4.1.2  IATF 16949 Internal Pre-Audit

4.2  Production Ramp-Up & Closure

4.2.1  Operator Training

4.2.2  Production Ramp-Up to Full Throughput

4.2.3  Project Closure & Handover

3. Numbering & Coding Convention

The WBS uses a standard three-level numeric code, consistent across the Project Schedule, Cost Baseline, WBS Dictionary, and RACI Matrix:

| Level | Example Code | Represents |
| --- | --- | --- |
| 1 | 1.0, 2.0, 3.0, 4.0 | Phase — the four major stages of Project Alcatraz |
| 2 | 1.1, 2.1, 3.1 | Deliverable — a distinct output within a phase (e.g., 'Equipment Procurement') |
| 3 | 1.1.1, 2.1.1 | Work package — the lowest level; where duration, cost, and a single owner are assigned |

4. WBS Dictionary (Summary Reference)

The full WBS Dictionary is maintained in the companion spreadsheet (WBS_Dictionary_Alcatraz_Falcon.xlsx), with one row per WBS element defining its description, deliverables, acceptance criteria, owner, estimated duration and cost, and dependencies. A condensed excerpt is shown below.

| WBS ID | Element Name | Description | Owner |
| --- | --- | --- | --- |
| 1.1.1 | Develop Project Charter | Draft, review, and obtain Sponsor sign-off on the Project Charter | Ricardo Palacio Serra |
| 2.1.1 | Issue Purchase Orders | Issue POs for SMT printer, pick-and-place, reflow oven, and AOI system | Mariana Solís |
| 3.1.1 | Install SMT Line Equipment | Physical installation and mechanical setup of core SMT equipment | Carlos Medina |
| 4.1.1 | First Article Inspection | Conduct and document FAI to confirm the line meets quality requirements | Daniela Cortés |

5. Approval Signatures

| Name / Role | Signature | Date |
| --- | --- | --- |
| Angélica Navarro / Sponsor |  |  |
| Ricardo Palacio Serra / Project Manager |  |  |
| Fernando Ibarra / Plant Manager |  |  |

6. Version / Revision History

| Version | Date | Author | Change Description |
| --- | --- | --- | --- |
| 1.0 | 01/09/2026 | Ricardo Palacio Serra | Initial draft, developed during project kickoff workshop |