## Sprint Burndown
[ORGANIZATION NAME]
SPRINT BURNDOWN
[Product / Project Name] — Sprint [#]
Track remaining work (in Story Points or hours -- pick one unit and stay consistent) across the Sprint. Enter the Sprint's total committed work, then record Actual Remaining at the end of each day. The Ideal line is calculated automatically as a straight-line burn to zero.
Sprint Length (working days): |  | 10
Total Committed (points/hrs): |  | 40
Day | Date | Ideal Remaining | Actual Remaining
0 | [Date 0] | 40 | 40
1 | [Date 1] | 36
2 | [Date 2] | 32
3 | [Date 3] | 28
4 | [Date 4] | 24
5 | [Date 5] | 20
6 | [Date 6] | 16
7 | [Date 7] | 12
8 | [Date 8] | 8
9 | [Date 9] | 4
10 | [Date 10] | 0
vitruvioconsultores.net

## Release Burnup
[ORGANIZATION NAME]
RELEASE BURNUP
[Product / Project Name] — Release [#]
Unlike Burndown, Burnup tracks TWO lines: Total Scope (everything committed to the release) and Completed (work actually finished), both trending upward across Sprints. This makes scope changes visible -- if Total Scope rises mid-release, that's scope creep, and the gap between the two lines is the work still remaining.
Sprint | Date | Total Scope (Story Points) | Completed (Story Points) | Notes
0 | [Date Sprint 0] | 80 | 0 | Release baseline
1 | [Date Sprint 1] | 80 | 18
2 | [Date Sprint 2] | 80 | 34
3 | [Date Sprint 3] | 95 | 34 | Scope added mid-release
4 | [Date Sprint 4] | 95 | 50
5 | [Date Sprint 5] | 95 | 68
6 | [Date Sprint 6] | 95 | 82
7 | [Date Sprint 7] | 95 | 95 | Release complete
vitruvioconsultores.net

## Instructions
[ORGANIZATION NAME]
BURNDOWN / BURNUP TRACKER — INSTRUCTIONS
Burndown vs. Burnup — What's the Difference?
Sprint Burndown | Tracks REMAINING work only, day by day, within a single Sprint. Simple and quick to read, but cannot show whether scope changed mid-Sprint -- a flat line could mean 'no progress' or 'work was added to replace what was finished.'
Release Burnup | Tracks BOTH total scope and completed work, Sprint by Sprint, across a Release. Because it shows two lines instead of one, it makes scope changes visible: if the Total Scope line rises, scope was added; the gap between the two lines is what's left to do.
When to use which | Use Burndown for day-to-day Sprint tracking (Daily Scrum conversations). Use Burnup for Release-level or longer-horizon tracking, especially when stakeholders need to see whether scope is creeping.
Using the Sprint Burndown Tab
1. Set 'Sprint Length' and 'Total Committed' (in Story Points or hours -- pick one unit and use it consistently across all trackers).
2. Fill in the Date column for each Sprint day.
3. At the end of each day, enter the team's total remaining work into that day's 'Actual Remaining' cell.
4. The Ideal line is calculated automatically. If Actual trends above Ideal, the team is behind pace -- use this to prompt conversation at the Daily Scrum, not as a performance metric.
Using the Release Burnup Tab
1. At the start of the release, record Sprint 0 as the baseline: Total Scope = everything committed at kickoff, Completed = 0.
2. At the end of each Sprint, add a row: update Total Scope only if items were added or removed from the release, and update Completed with cumulative finished Story Points.
3. Use the Notes column to flag WHY scope changed (e.g., 'Epic X added per stakeholder request') -- the chart shows THAT it changed, the notes explain why.
4. The release is complete when the Completed line meets the Total Scope line.
vitruvioconsultores.net