## Configuration Item Register
FALCON ELECTRONICS
CONFIGURATION ITEM REGISTER
Project Alcatraz — SMT Production Line Installation
Prepared By: Ricardo Palacio Serra / Project Manager ¦ Date: 01/09/2026 ¦ Version: 1.0
Item ID | Item Name | Type | Current Version | Baseline Status | Related WBS ID | Owner | Last Updated | Related Change ID | Storage Location
CI-001 | Project Charter — Project Alcatraz | Document | 1.0 | Baselined | 1.1.1 | Ricardo Palacio Serra | 01/09/2026 |  | SharePoint/Alcatraz/Governance/Charter_v1.0.docx
CI-002 | Project Scope Statement — Project Alcatraz | Document | 1.0 | Baselined | 1.1.1 | Ricardo Palacio Serra | 01/09/2026 |  | SharePoint/Alcatraz/Governance/ScopeStatement_v1.0.docx
CI-003 | SMT Line Equipment Technical Specification | Equipment Spec | 1.0 | Baselined | 2.1.1 | Mariana Solís | 05/09/2026 |  | SharePoint/Alcatraz/Procurement/EquipSpec_SMTLine_v1.0.pdf
CI-004 | AOI System Technical Specification | Equipment Spec | 1.0 | Baselined | 2.1.1 | Mariana Solís | 05/09/2026 |  | SharePoint/Alcatraz/Procurement/EquipSpec_AOI_v1.0.pdf
CI-005 | Electrical & Compressed Air Design Drawings | Design | 1.1 | Under Change | 2.2.1 | Luis Beltrán | 20/09/2026 | CR-004 | SharePoint/Alcatraz/Facilities/ElectricalAirDesign_v1.1.dwg
CI-006 | Facility Layout Floor Plan | Design | 1.0 | Baselined | 2.2.2 | Fernando Ibarra | 12/09/2026 |  | SharePoint/Alcatraz/Facilities/FloorPlan_v1.0.dwg
CI-007 | MES Integration Configuration Specification | Document | 0.1 | Draft | 3.2.1 | Sofía Reyes | 15/09/2026 |  | SharePoint/Alcatraz/IT/MESConfigSpec_v0.1.docx
CI-008 | IPC-A-610 Class 3 Acceptance Criteria (Customer-Adopted) | Document | 1.0 | Baselined | 4.1.1 | Daniela Cortés | 01/09/2026 |  | SharePoint/Alcatraz/Quality/IPC610_AcceptanceCriteria_v1.0.pdf
CI-009 | First Article Inspection (FAI) Protocol | Document | 1.0 | Baselined | 4.1.1 | Daniela Cortés | 15/09/2026 |  | SharePoint/Alcatraz/Quality/FAIProtocol_v1.0.docx
CI-010 | IATF 16949 Internal Pre-Audit Checklist | Document | 1.0 | Baselined | 4.1.2 | Daniela Cortés | 01/09/2026 |  | SharePoint/Alcatraz/Quality/IATF_PreAuditChecklist_v1.0.docx
CI-011 | Operator Training Manual — SMT Line | Document | 0.1 | Draft | 4.2.1 | Fernando Ibarra | 20/09/2026 |  | SharePoint/Alcatraz/Training/OperatorManual_v0.1.docx
CI-012 | IATF 16949 Qualification Package (Customer Submission) | Document | 0.1 | Draft | 4.1.2 | Daniela Cortés | 22/09/2026 |  | SharePoint/Alcatraz/Quality/IATF_QualPackage_v0.1.docx
vitruvioconsultores.net